## Slide 1: Self-Budgeting Application Transition from Waterfall to Scrum
Chaitanya Durgesh Nynavarapu - A20561894
Niranajaan Veeraraghavan Munuswamy - A20552057
Dresha Reddy Bommana - A20546970
Ashish Reddy Thumu - 20560560

## Slide 2: Introduction to Transition:
The Self-Budgeting Application helps users track income, expenses, set budgets, and create financial reports. Transitioning from Waterfall to Scrum allows for continuous feedback and iterative development, providing greater flexibility.

## Slide 3: Review of Phase 1 Waterfall Plan
In Phase 1, Waterfall methodology was used with stages for Requirements, Design, Implementation, Testing, and Documentation.
Key areas identified for adaptation:
Increased flexibility.
Improved user feedback loops.
Iterative progress and refinement.

## Slide 4: Scrum Team Structure
Roles:
  Product Owner: Manages backlog and sets priorities.
  Scrum Master: Facilitates Scrum events, ensures process adherence.
  Development Team: Developers, QA Engineers, UI/UX Designers.
  DevOps Engineer: Ensures smooth deployment.
These roles support iterative budgeting feature delivery and feedback integration.

## Slide 5: Developing the Product Backlog
Converted Waterfall requirements to user stories:
  'Track daily expenses by category to monitor spending.'
  'Set monthly budgets and receive alerts when nearing limits.'
Stories are prioritized based on business value and user impact.

## Slide 6: Sprint Planning and Initial Sprints
Sprint Length: 2 weeks
Sprint Goals:
  Sprint 1: Income tracking setup and initial UI.
  Sprint 2: Expense tracking and category features.
  Sprint 3: Budget setting, notifications for budget limits.
  Sprint 4: Testing, feedback incorporation, documentation.

## Slide 7: Outline of Scrum Events :
Core Scrum Events:
  Sprint Planning: Define goals and sprint backlog.
  Daily Scrums: Progress updates and addressing blockers.
  Sprint Review: Present increments and gather feedback.
  Sprint Retrospective: Reflect on improvements for the next sprint.

## Slide 8: Defining Scrum Artifacts
Scrum Artifacts for Self-Budgeting Application:
  Product Backlog: List of all budgeting-related features.
  Sprint Backlog: Items selected for the current Sprint.
  Increment: Budgeting features completed each Sprint.

## Slide 9: Estimation Techniques
Estimation using story points:
  Story points based on complexity and effort required.
Tasks are sized relative to one another, enabling consistent planning across sprints.
Effort = Work / Productivity Rate

## Slide 10: Designing the Scrum Board
The Scrum board has columns for:
To Do
In Progress
Testing
Done
The board visualizes task progress throughout each sprint.

## Slide 11: Definition of Done :
Criteria for 'Done':
  Code meets standards and passes tests
  Integrated with other features
  Documentation updated
Ensures consistency and completion across sprints.

## Slide 12: Developing a CI/CD Plan
The CI/CD plan supports iterative development:
  Continuous Integration: Regularly merging and testing code
  Continuous Deployment: Automating releases based on approvals
Enables seamless deployment of incremental budgeting features.

## Slide 13: Analysis Report: Waterfall vs. Scrum
Waterfall vs. Scrum for Self-Budgeting Application:
  Scrum provides flexibility, early feedback, and adaptability.
  Waterfall limits iterative refinement.
Scrum aligns with the needs of iterative financial management.

## Slide 14: Metrics and Reporting
Key Performance Indicators (KPIs):
  Sprint Velocity: Measures team productivity
  Defect Density: Ensures quality control
  User Feedback: Tracks user satisfaction and app functionality
Tracking these metrics supports continuous improvement.

## Slide 15: Output

## Slide 16: Conclusion
Scrum’s iterative and flexible nature benefits budgeting app development by allowing:
  Early feedback
  Adaptive planning
  Incremental delivery of critical budgeting features.
Expected outcomes include improved flexibility, better feedback integration, and enhanced user satisfaction.